## WBS Electrical
WORK BREAKDOWN STRUCTURE (WBS) ELECTRICAL
Project : Robot Manipulator Lengan 6-DOF Untuk Pengelasan | [8 empty] | Due Date : 9 Maret 2025
Level | Code | Sub Code | Main Task | Task | Sub Task | Notes | PIC | Is Done | Task Progress | Total Progress
1 | 1.1 | 1.1.1 | Pembuatan Teach Pendant | Pembuatan PCB | Desain schematic |  | Alfon | TRUE | 100% | 100%
|  | 1.1.2 |  |  | Desain board |  |  | TRUE
|  | 1.2.3 |  |  | Pencetakan PCB |  |  | TRUE
|  | 1.1.3 |  |  | Listing komponen PCB |  |  | TRUE
|  | 1.1.4 |  |  | Pembelian komponen PCB |  |  | TRUE
|  | 1.2.4 |  |  | Perakitan komponen |  |  | TRUE
| 1.2 | 1.2.1 |  | Pengujian PCB | Pengujian daya |  |  | TRUE
|  | 1.2.2 |  |  | Pengujian komunikasi RS-232 |  |  | TRUE
|  | 1.2.3 |  |  | Pengujian LCD |  |  | TRUE
|  | 1.2.4 |  |  | Pengujian keypad |  |  | TRUE
|  | 1.2.5 |  |  | Pengujian EEPROM |  |  | TRUE
|  | 1.2.6 |  |  | Pengujian emergency stop |  |  | TRUE
| 1.3 | 1.3.1 |  | Pembuatan Case | Desain top case |  |  | TRUE
|  | 1.3.2 |  |  | Desain bottom case |  |  | TRUE
|  | 1.3.3 |  |  | Pencetakan top & bottom case |  | Gilar | TRUE
| 1.4 | 1.4.1 |  | Perakitan | Pemasangan PCB |  | Alfon | TRUE
|  | 1.4.2 |  |  | Pemasangan komponen antarmuka |  |  | TRUE
|  | 1.4.3 |  |  | Pemasangan komponen daya |  |  | TRUE
|  | 1.4.4 |  |  | Pemasangan top & bottom case |  |  | TRUE
2 | 2.1 | 2.1.1 | Pembuatan Kontroler Utama | Pembuatan PCB | Desain schematic |  | Alfon | TRUE | 100%
|  | 2.1.2 |  |  | Desain board |  |  | TRUE
|  | 2.1.3 |  |  | Evaluasi desain |  |  | TRUE
|  | 2.1.4 |  |  | Listing komponen PCB |  |  | TRUE
|  | 2.1.5 |  |  | Pembelian komponen |  |  | TRUE
|  | 2.1.6 |  |  | Pencetakan PCB |  |  | TRUE
|  | 2.1.7 |  |  | Perakitan komponen |  |  | TRUE
| 2.2 | 2.2.1 |  | Pengujian PCB | Pengujian daya |  |  | TRUE
|  | 2.2.2 |  |  | Pengujian komunikasi RS-232 |  |  | TRUE
|  | 2.2.3 |  |  | Pengujian kontrol motor stepper |  |  | TRUE
|  | 2.2.4 |  |  | Pengujian pembacaan encoder |  |  | TRUE
|  | 2.2.5 |  |  | Pengujian interface |  |  | TRUE
|  | 2.2.6 |  |  | Pengujian EEPROM |  |  | TRUE
|  | 2.2.7 |  |  | Pengujian emergency stop |  |  | TRUE
|  | 2.2.8 |  |  | Pengujian penuh |  |  | TRUE
| 2.3 | 2.3.1 |  | Pembuatan Bracket PCB | Desain bracket |  | Gilar | TRUE
|  | 2.3.2 |  |  | Pencetakan bracket |  |  | TRUE
3 | 3.1 | 3.1.1 | Pembuatan Panel Kontrol | Desain Pengawatan | Komponen daya |  | Alfon | TRUE | 100%
|  | 3.1.2 |  |  | Komponen kontrol |  |  | TRUE
| 3.2 | 3.2.1 |  | Desain Hole Position | Penentuan socket konektor ke manipulator |  |  | TRUE
|  | 3.2.2 |  |  | Listing komponen panel |  |  | TRUE
|  | 3.2.3 |  |  | Pembelian komponen panel |  |  | TRUE
|  | 3.2.4 |  |  | Pengukuran komponen panel |  |  | TRUE
|  | 3.2.5 |  |  | Pembuatan desain hole position |  |  | TRUE
| 3.3 | 3.3.1 |  | Perakitan Panel Kontrol | Pembuatan lubang hole panel |  | Alfon, Gilar, Esa, Imam | TRUE
|  | 3.3.2 |  |  | Pemasangan komponen daya |  |  | TRUE
|  | 3.3.3 |  |  | Pengawatan komponen daya |  |  | TRUE
|  | 3.3.4 |  |  | Pemasangan komponen kontrol |  |  | TRUE
|  | 3.3.5 |  |  | Pengawatan komponen kontrol |  |  | TRUE
| 3.4 | 3.4.1 |  | Pengujian Panel Kontrol | Pengujian daya |  | Alfon | TRUE
|  | 3.4.2 |  |  | Pengujian komponen pengaman |  |  | TRUE
4 | 4.1 | 4.1.1 | Pembuatan Konektor Utama | Pembuatan PCB | Desain schematic |  |  | TRUE | 100%
|  | 4.1.2 |  |  | Desain board |  |  | TRUE
|  | 4.1.3 |  |  | Evaluasi desain |  |  | TRUE
|  | 4.1.4 |  |  | Listing komponen PCB |  |  | TRUE
|  | 4.1.5 |  |  | Pembelian komponen |  |  | TRUE
|  | 4.1.6 |  |  | Pencetakan PCB |  |  | TRUE
|  | 4.1.7 |  |  | Perakitan komponen |  |  | TRUE
| 4.2 | 4.2.1 |  | Pengujian PCB | Pengujian daya |  |  | TRUE
|  | 4.2.2 |  |  | Pengujian konektivitas |  |  | TRUE

## WBS Mechanical
WORK BREAKDOWN STRUCTURE (WBS) MECHANICAL
Project : Robot Manipulator Lengan 6-DOF Untuk Pengelasan | [10 empty] | Due Date : 9 Maret 2025
Level | Code | Sub Code |  | Main Task | Task | Sub Task |  | Notes | PIC | Is Done | Task Progress | Total Progress
1 | 1.1 | 1.1.1 |  | Perancangan Robot | Rough Design | Pengukuran Bak (Obyek Pengelasan) |  |  |  | TRUE | 100% | 100%
|  | 1.1.2 |  |  |  | Penentuan Dimensi Robot |  |  |  | TRUE
|  | 1.1.3 |  |  |  | Perancangan Desain Kasar |  |  |  | TRUE
|  | 1.1.4 |  |  |  | Analisis FEA untuk Mengetahui Kebutuhan Torsi dan Gear Ratio |  |  |  | TRUE
| 1.2 | 1.2.1 |  |  | Perancangan Struktur Utama | Penentuan Jenis dan Ukuran Bearings dan Belts |  |  |  | TRUE
|  | 1.2.2 |  |  |  | Pembelian Bearings dan Belts |  |  |  | TRUE
|  | 1.2.3 |  |  |  | Perancangan Desain Struktur Robot |  |  |  | TRUE
|  | 1.2.4 |  |  |  | Analisis FEA untuk Mengetahui Kekuatan Desain Final |  |  |  | TRUE
| 1.3 | 1.3.1 |  |  | Perancangan Desain Cover | Perancangan Cable Management Robot |  |  |  | TRUE
|  | 1.3.2 |  |  |  | Perancangan Connector Housing Robot |  |  |  | TRUE
|  | 1.3.3 |  |  |  | Perancangan Cover Body |  |  |  | TRUE
| 1.4 | 1.4.1 |  |  | Perancangan End Effector | Pembongkaran dan Pengukuran MIG Welding |  |  |  | TRUE
|  | 1.4.2 |  |  |  | Perancangan Desain Mounting End Effector |  |  |  | TRUE
2 | 2.1 | 2.1.1 |  | Manufaktur | CNC Milling | Listing Materials Machining |  |  |  | TRUE | 100%
|  | 2.1.2 |  |  |  | Pembelian Materials Machining |  |  |  | TRUE
|  | 2.1.3 | 2.1.3.1 |  |  | Perancangan Jig Machining | Jig As |  |  | TRUE
|  |  | 2.1.3.2 |  |  |  | Jig Tangent |  |  | TRUE
|  |  | 2.1.3.3 |  |  |  | Jig Perpendicular |  |  | TRUE
|  | 2.1.4 | 2.1.4.1 |  |  | Pembuatan Jig Machining | Jig As |  |  | TRUE
|  |  | 2.1.4.2 |  |  |  | Jig Tangent |  |  | TRUE
|  |  | 2.1.4.3 |  |  |  | Jig Perpendicular |  |  | TRUE
|  | 2.1.5 | 2.1.5.1 |  |  | CAM Toolpath, Machining, and Tapping | J1 Base Plate |  |  | TRUE
|  |  | 2.1.5.2 |  |  |  | J1 Tension Bracket |  |  | TRUE
|  |  | 2.1.5.3 |  |  |  | J1 Base Bracket |  |  | TRUE
|  |  | 2.1.5.4 |  |  |  | J1 Spindle Housing |  |  | TRUE
|  |  | 2.1.5.5 |  |  |  | J1 Spindle Turret |  |  | TRUE
|  |  | 2.1.5.6 |  |  |  | J1 Turret Platform |  |  | TRUE
|  |  | 2.1.5.7 |  |  |  | J1 Spindle Bracket |  |  | TRUE
|  |  | 2.1.5.8 |  |  |  | J2 Spindle Housing |  |  | TRUE
|  |  | 2.1.5.9 |  |  |  | J2 Spindle Bracket |  | Hardening steel? | TRUE
|  |  | 2.1.5.10 |  |  |  | J2 Motor Bracket Bottom |  |  | TRUE
|  |  | 2.1.5.11 |  |  |  | J2 Motor Support Bottom |  |  | TRUE
|  |  | 2.1.5.12 |  |  |  | J2 Motor Bracket Top |  |  | TRUE
|  |  | 2.1.5.13 |  |  |  | J2 Motor Support Top |  |  | TRUE
|  |  | 2.1.5.14 |  |  |  | J2 Spindle Turret |  |  | TRUE
|  |  | 2.1.5.15 |  |  |  | J2 Bottom Arm |  |  | TRUE
|  |  | 2.1.5.16 |  |  |  | J3 Spindle Housing |  |  | TRUE
|  |  | 2.1.5.17 |  |  |  | J3 Spindle Turret |  |  | TRUE
|  |  | 2.1.5.18 |  |  |  | J3 Turret Platform |  |  | TRUE
|  |  | 2.1.5.19 |  |  |  | J3 Spindle Bracket |  |  | TRUE
|  |  | 2.1.5.20 |  |  |  | J4 Front Housing |  |  | TRUE
|  |  | 2.1.5.21 |  |  |  | J4 Rear Housing |  |  | TRUE
|  |  | 2.1.5.22 |  |  |  | J5 Motor Mount |  |  | TRUE
|  |  | 2.1.5.23 |  |  |  | J4 Mount Right |  |  | TRUE
|  |  | 2.1.5.24 |  |  |  | J4 Mount Left |  |  | TRUE
|  |  | 2.1.5.25 |  |  |  | J4 Mount Center |  |  | TRUE
|  |  | 2.1.5.26 |  |  |  | J5 Pipe Housing |  |  | TRUE
|  |  | 2.1.5.27 |  |  |  | J5 Top Arm |  |  | TRUE
|  |  | 2.1.5.28 |  |  |  | J5 Lead Screw Housing |  |  | TRUE
|  |  | 2.1.5.29 |  |  |  | J5 Bearing Stopper |  |  | TRUE
|  |  | 2.1.5.30 |  |  |  | J5 Idler Tension |  |  | TRUE
|  |  | 2.1.5.31 |  |  |  | J5 Bearing Post |  |  | TRUE
|  |  | 2.1.5.32 |  |  |  | J5 Spindle Housing |  |  | TRUE
|  |  | 2.1.5.33 |  |  |  | J5 Turret Platform |  |  | TRUE
|  |  | 2.1.5.34 |  |  |  | J5 Spindle Turret |  |  | TRUE
|  |  | 2.1.5.35 |  |  |  | J5 Spindle Bracket |  |  | TRUE
|  |  | 2.1.5.36 |  |  |  | J6 Motor Mount A |  |  | TRUE
|  |  | 2.1.5.37 |  |  |  | J6 Motor Mount B |  |  | TRUE
|  |  | 2.1.5.38 |  |  |  | J4 Main Shaft |  |  | TRUE
| 2.2 | 2.2.1 |  |  | 3D Print | Pembelian Filament |  |  |  | TRUE
|  | 2.2.2 | 2.2.2.1 |  |  | CAM Slicing and Printing | J1 Pulley |  |  | TRUE
|  |  | 2.2.2.2 |  |  |  | J3 Pulley |  |  | TRUE
|  |  | 2.2.2.3 |  |  |  | J4 Pulley |  |  | TRUE
|  |  | 2.2.2.4 |  |  |  | J5 Pulley |  |  | TRUE
|  |  | 2.2.2.5 |  |  |  | J5 Motor Mount |  |  | TRUE
|  |  | 2.2.2.6 |  |  |  | Cover Body |  |  | TRUE
| 2.3 | 2.3.1 |  |  | Assembly | List Components |  |  |  | TRUE
|  | 2.3.2 |  |  |  | List Fasteners |  |  |  | TRUE
|  | 2.3.3 |  |  |  | Pembelian Components |  |  |  | TRUE
|  | 2.3.4 |  |  |  | Pembelian Fasteners |  |  |  | TRUE
|  | 2.3.5 |  |  |  | Proses Assembly |  |  |  | TRUE
3 | 3.1 | 3.1.1 |  | Pengujian dan Troubleshoot | Pengujian | Pengujian Rigiditas |  |  |  | TRUE | 100%
|  | 3.1.2 |  |  |  | Pengujian Beban |  |  |  | TRUE
| 3.2 | 3.2.1 |  |  | Troubleshoot | Troubleshoot |  |  |  | TRUE
|  | 3.2.2 |  |  |  | Revisi |  |  |  | TRUE

## WBS Program
WORK BREAKDOWN STRUCTURE (WBS) PROGRAM
Project : Robot Manipulator Lengan 6-DOF Untuk Pengelasan | [8 empty] | Due Date : 20 April 2025
Level | Code | Sub Code | Main Task | Task | Sub Task | Notes | PIC | Is Done | Task Progress | Total Progress
1 | 1.1 | 1.1.1 | Program Teach Pendant | Improve Menu | Handler emergency stop |  | Alfon | TRUE | 50% | 36.11%
|  | 1.1.2 |  |  | Revisi input speed menu welding dan mapping |  |  | TRUE
|  | 1.1.3 |  |  | Handler pengiriman homing saat emergency | TERTUNDA |  | FALSE
| 1.2 | 1.2.1 |  | Komunikasi RS-232 | Penyesuaian variabel input speed |  |  | FALSE
2 | 2.1 | 2.1.1 | Program Kontroler Utama | Kinematika Robot | Handler inverse kinematic |  |  | FALSE | 22.22%
|  | 2.1.2 |  |  | Handler forward kinematic |  |  | FALSE
|  | 2.1.3 |  |  | Handler deteksi singularitas |  |  | FALSE
|  | 2.1.4 |  |  | Handler interpolasi |  |  | FALSE
|  | 2.1.5 |  |  | Handler adaptive move speed |  |  | FALSE
| 2.2 | .2.2.1 |  | Kontrol Robot | Kontrol gerak continuous saat joint mode |  |  | TRUE
|  | 2.2.2 |  |  | Kontrol gerak by distance saat joint mode |  |  | TRUE
|  | 2.2.3 |  |  | Kontrol gerak continuous saat cartesian mode | TERTUNDA |  | FALSE
|  | 2.2.4 |  |  | Kontrol gerak by distance saat cartesian mode |  |  | FALSE

## Electrical Component List
COMPONENT LIST ELECTRICAL
No | Name | Part | Componenct | Brand | Specs | Quantity | Bought | Progress
1 | Control Panel | Power | Push button start (green) | EWIG | 22mm, 220VAC, NO NC | 1 | TRUE | 100%
|  |  | Push button stop (red) |  |  | 1 | TRUE
|  |  | Emergency stop button |  |  | 1 | TRUE
|  |  | Pilot lamp green | Fort | 220VAC | 1 | TRUE
|  |  | Pilot lamp red |  |  | 1 | TRUE
|  |  | Pilot lamp yellow |  |  | 1 | TRUE
|  |  | Digital avometer for panel box | Larkin | 22mm, 250VAC, 16A | 1 | TRUE
|  |  | Shuko socket panel mount | Mennekes | 2Pole + E, 16A 250VAC | 1 | TRUE
|  |  | Power supply DC | - | 24V 30A | 1 | TRUE
|  |  | AC Contactor 220V | Chint | 1NO 1NC | 1 | TRUE
|  |  | MCB AC 220V |  | 2 Pole | 1 | TRUE
|  |  | Terminal blok | - | 6 Pole, 25A | 2 | TRUE
|  |  | Tie Mount |  | 20x20mm | 50 | TRUE
|  |  | Din rail |  | 1m | 1 | TRUE
|  |  | Schuko plug male | DV | 16A, 250VAC | 2 | TRUE
|  |  | NYMHY 3x1,5mm | Wilson | 10m | 1 | TRUE
|  | Control | Main controller | Custom | 24VDC | 1 | TRUE
|  |  | TB6600 Stepper motor driver | Toshiba | 40V 6A | 6 | TRUE
|  |  | Kebel AWG 20 Merah | - | 30m | 1 | TRUE
|  |  | Kebel AWG 20 Hitam |  |  |  | TRUE
|  |  | Kebel AWG 20 Hijau |  |  |  | TRUE
|  |  | Kebel AWG 20 Biru |  |  |  | TRUE
|  |  | Kebel AWG 20 Kuning |  |  |  | TRUE
|  |  | Kabel AWG 20 Putih |  |  |  | TRUE
|  |  | Skun ferulles 0,5mm - Merah |  | 100 pcs | 1 | TRUE
|  |  | Skun ferulles 0,5mm - Hitam |  |  |  | TRUE
|  |  | Skun ferulles 0,5mm - Biru |  |  |  | TRUE
|  |  | Skun ferulles 0,5mm - Kuning |  |  |  | TRUE
|  |  | Skun ferulles 0,5mm - Putih |  | 10 pcs |  | TRUE
|  |  | Skun ferulles 1,5mm - Merah |  | 20 pcs |  | TRUE
|  |  | Skun ferulles 1,5mm - Hitam |  |  |  | TRUE
|  |  | SSR DC | Fotek | 40A | 2 | TRUE
|  | Connectors | GX-16 connector male female | - | 6 pin | 1 | TRUE
|  |  | Heavy duty connectors set | ? | 24 pin | 1 | TRUE
|  | Other | Panel box | - | 60cm x 50cm | 1 | TRUE
|  |  | Cable duct | - | 25mm x 25mm, 2m | 1 | TRUE
|  |  | Bolt M4 | - | 20mm | 30 | TRUE
|  |  | Bolt M3 | - | 20mm | 10 | TRUE
|  |  | Nut M4 | - | - | 30 | TRUE
|  |  | Nut M3 | - | - | 10 | TRUE
2 | Teach Pendant | Power | Emergency stop button | DV | 16mm, 220VAC, 2NO 2NC | 1 | TRUE | 100%
|  |  | Switch button |  | 16mm 220VAC, NO NC | 1 | TRUE
|  |  | GX16 connector male female | - | 6 pin | 1 | TRUE
|  |  | Cable multicore | - | 6 core, 2m | 1 | TRUE
|  | PCB | STM32F103C8T6 | STM | 72MHz | 1 | TRUE
|  |  | LM2596-5V | TI | 5V 3A max | 1 | TRUE
|  |  | LM2596-2,2V |  | 3,3V 3A max | 1 | TRUE
|  |  | EEPROM AT24C256 | Atmel | 256Kbyte | 1 | TRUE
|  |  | Resistor SMD 1k Ohm | - | 0805 Package | 1 | TRUE
|  |  | Resistor SMD 10k Ohm |  |  | 3 | TRUE
|  |  | Resistor SMD 100 Ohm |  |  | 2 | TRUE
|  |  | Resistor SMD 470 Ohm |  |  | 1 | TRUE
|  |  | Kapasitor SMD 100nF |  |  | 6 | TRUE
|  |  | Kapasitor SMD 1uF |  |  | 1 | TRUE
|  |  | Kapasitor SMD 470nF |  |  | 3 | TRUE
|  |  | LED SMD Red |  |  | 4 | TRUE
|  |  | LED SMD Blue |  |  | 1 | TRUE
|  |  | LED SMD Green |  |  | 1 | TRUE
|  |  | Elco SMD 470uF |  | 1010 Package | 1 | TRUE
|  |  | Induktor SMD 33uH |  | 1260 Package | 1 | TRUE
|  |  | Induktor SM 22uH |  |  | 1 | TRUE
|  |  | PC817 | Sharp | SOIC Package | 1 | TRUE
|  |  | MAX3232 | TI |  | 1 | TRUE
|  |  | SS34 Diode | Vishay | SMB Package | 2 | TRUE
|  |  | JST 6pin | - | XH version | 1 | TRUE
|  |  | JST 4pin |  |  | 1 | TRUE
|  |  | JST 2pin |  |  | 1 | TRUE
|  | Interface | LCD 20x4 | Vishay | Green | 1 | TRUE
|  |  | PCF8574 | TI | SOIC Package | 1 | TRUE
|  |  | Keypad matrix 5x4 | - | - | 1 | TRUE
|  | Case | Pendant top case | Custom | Sunlu PLA+ Ver2 | 1 | TRUE
|  |  | Pendant bottom case |  |  | 1 | TRUE
|  |  | Bolt 10mm | - | M3 | 6 | TRUE
|  |  | Bolt 5mm |  |  | 4 | TRUE
3 | Arm Manipulator | Actuators | Motor stepper NEMA 23HS7628 | Hanpose | 18,9Kg/cm | 3 | TRUE | 100%
|  |  | Motor stepper NEMA 23HS5628 |  | 12,6Kg/cm | 2 | TRUE
|  |  | Motor stepper NEMA 23HS10028 |  | 30Kg/cm | 1 | TRUE
|  | Sensors | Limit switch | Omron | 125VDC NO NC | 6 | TRUE
|  |  | Bolt M2.5 | - | 4mm | 24 | TRUE
|  |  | Magnetic Encoder AS5600 |  | 12bit I2C | 6 | TRUE
|  | Power | Heavy duty connector set |  | 48 pin | 1 | TRUE
|  |  | Gland cable PG29 |  | 18mm - 25mm | 4 | TRUE
|  |  | Konektor JST set 2 pin |  |  | 7 | TRUE
|  |  | Konektor JST set 4 pin |  |  | 18 | TRUE
|  |  | Konektor JST set 6 Pin |  |  | 4 | TRUE
|  |  | Cable sleeve 4mm / 1m |  | Braided | 1 | TRUE
|  |  | Cable sleeve 18mm / 1m |  |  | 1 | TRUE
|  |  | Cable sleeve spiral / 10m |  | Hitam | 1 | TRUE
4 | Main Controller | PCB | SMT32H743VIT6 | STM | 480MHz | 1 | TRUE | 100%
|  |  | LM2596-5V | TI | 5V 3A max | 1 | TRUE
|  |  | LM2596-2,2V |  | 3,3V 3A max | 1 | TRUE
|  |  | EEPROM AT24C512 | Atmel | 512Kbyte | 2 | TRUE
|  |  | Resistor SMD 1k Ohm | - | 0805 Package | 1 | TRUE
|  |  | Resistor SMD 10k Ohm |  |  | 37 | TRUE
|  |  | Resistor SMD 100 Ohm |  |  | 22 | TRUE
|  |  | Resistor SMD 470 Ohm |  |  | 1 | TRUE
|  |  | Resistor SMD 220 Ohm |  |  | 6 | TRUE
|  |  | Kapasitor SMD 100nF |  |  | 7 | TRUE
|  |  | Kapasitor SMD 1uF |  |  | 1 | TRUE
|  |  | Kapasitor SMD 470nF |  |  | 3 | TRUE
|  |  | LED SMD Red |  |  | 1 | TRUE
|  |  | LED SMD Blue |  |  | 1 | TRUE
|  |  | LED SMD Green |  |  | 1 | TRUE
|  |  | Elco SMD 470uF |  | 1010 Package | 4 | TRUE
|  |  | Elco 1000uF |  | 35V 8mm Pitch | 1 | TRUE
|  |  | Induktor SMD 33uH |  | 1260 Package | 1 | TRUE
|  |  | Induktor SM 22uH |  |  | 1 | TRUE
|  |  | PC817 | Sharp | SOIC Package | 27 | TRUE
|  |  | MAX3232 | TI |  | 1 | TRUE
|  |  | SS34 Diode | Vishay | SMB Package | 2 | TRUE
|  |  | LCD OLED | - | 128 x 64 | 1 | TRUE
|  |  | Terminal Blok 4 Pin |  | Plugable L Shape | 2 | TRUE
|  |  | Terminal Blok 6 Pin |  |  | 2 | TRUE
|  |  | Terminal Blok 8 Pin |  |  | 4 | TRUE
|  |  | Pin Header Female |  | 4x20 | 2 | TRUE
|  | PCB Case | PCB Mounting | Custom | Sunlu PLA+ Ver2 | 1 | TRUE
|  |  | Din Rail Bracket |  |  | 2 | TRUE
|  |  | Bolt M3 | - | 5mm | 4 | TRUE
|  |  | Bolt M3 |  | 10mm | 4 | TRUE
|  |  | Nut M3 |  | Normal | 4 | TRUE
[5 empty] | Insert | 4 | TRUE

## Mechanical Component List
COMPONENT LIST MECHANICAL
No | Name | Part | Componenct | Primary Specs | Secondary Specs | Quantity | Bought | Progress
| Actuators | Transmitions | Planetary Gearbox Reducer | NEMA 23 PX57 | Ratio 1:36 | 3 | TRUE | 100%
|  |  | Closed Loop Timing Belt | HTD3M W15 | 450mm | 2 | TRUE
|  |  | Closed Loop Timing Belt | HTD3M W25 | 351mm | 1 | TRUE
|  |  | Timing Belt per cm | HTD3M W25 | Steel Core | 22 | TRUE
|  |  | Timing Belt per cm | HTD3M W15 | Steel Core | 16 | TRUE
|  |  | Lead Screw | T8 | 500mm | 1 | TRUE
|  |  | Linear Shaft per cm | 6mm | Hard Chrome | 38 | TRUE
|  |  | T Nut | T8 | Brass Trapezoidal | 2 | TRUE
|  |  | Linear Bearing | LM6UU | 6(d) * 12(D) * 18(B/T) | 2 | TRUE
|  |  | Flexible Coupler | L25 | 6.35 * 8mm | 1 | TRUE
|  | Motors | Stepper Motor | NEMA 23 5718HB6401 | 30kgcm | 1 | TRUE
|  |  | Stepper Motor | NEMA 23 23HS8328 | 18.9kgcm | 3 | TRUE
|  |  | Stepper Motor | NEMA 23 23HS5628 | 12.6kgcm | 2 | TRUE
2 | Shaft | Bearings | Tapered Roller | 32016 | 80(d) * 125(D) * 29(B/T) | 2 | TRUE | 100%
|  |  | Tapered Roller | 32013 | 65 (d) * 100 (D) * 23 (B/T) | 2 | TRUE
|  |  | Tapered Roller | 30209 | 45(d) * 85(D) * 19(B/T) | 2 | TRUE
|  |  | Tapered Roller | 30206 | 30(d) * 62(D) * 16(B/T) | 1 | TRUE
|  |  | Needle Roller Thrust | AXK4565 | 45(d) * 58(D) * 5(B/T) | 2 | TRUE
|  |  | Needle Roller Thrust | AXK3552 | 35(d) * 52(D) * 5(B/T) | 1 | TRUE
|  |  | Needle Roller | HK4020 | 40(d) * 47(D) * 20(B/T) | 2 | TRUE
|  |  | Needle Roller | HK1612 | 16(d) * 22(D) * 12(B/T) | 2 | TRUE
|  |  | Deep Groove Ball | 688Z | 8(d) * 16(D) * 5(B/T) | 1 | TRUE
|  | Washers | Thrust | AS4565 | 45(d) * 56(D) * 5(B/T) | 4 | TRUE
|  |  | Thrust | AS3552 | 35(d) * 52(D) * 5(B/T) | 2 | TRUE
3 | Materials | Aluminium | Plate per cm^2 10mm thickness | 19*19cm | CNC Jig As | 361 | TRUE | 100%
|  |  | Plate per cm^2 10mm thickness | 19*27cm | J1 Base Plate | 513 | TRUE
|  |  | Plate per cm^2 10mm thickness | 5*5cm | J1 Tension Bracket | 25 | TRUE
|  |  | Plate per cm^2 10mm thickness | 19*27cm | J1 Base Bracket | 513 | TRUE
|  |  | As per cm 139.7mm diameter |  | J1 Spindle Housing | 7 | TRUE
|  |  | As per cm 82.55mm diameter |  | J1 Spindle Turret | 8 | TRUE
|  |  | Plate per cm^2 10mm thickness | 16*16cm | J1 Turret Platform | 256 | TRUE
|  |  | Plate per cm^2 10mm thickness | 13*13cm | J1 Spindle Bracket | 169 | TRUE
|  |  | Plate per cm^2 70mm thickness | 15*15cm | J2 Spindle Housing | 225 | TRUE
|  |  | Plate per cm^2 10mm thickness | 10*10cm | J2 Spindle Bracket | 100 | TRUE
|  |  | Plate per cm^2 10mm thickness | 10*8cm | J2 Motor Bracket Bottom | 80 | TRUE
|  |  | Plate per cm^2 10mm thickness | 10*9cm | J2 Motor Support Bottom | 90 | TRUE
|  |  | Plate per cm^2 10mm thickness | 10*6cm | J2 Motor Bracket Top | 60 | TRUE
|  |  | Plate per cm^2 10mm thickness | 10*6cm | J2 Motor Support Top | 60 | TRUE
|  |  | As per cm 69.85mm diameter |  | J2 Spindle Turret | 8 | TRUE
|  |  | Plate per cm^2 10mm thickness | 77*12cm | J2 Bottom Arm | 924 | TRUE
|  |  | As per cm 114.3mm diameter |  | J3 Spindle Housing | 6 | TRUE
|  |  | As per cm 50.8mm diameter |  | J3 Spindle Turret | 8 | TRUE
|  |  | Plate per cm^2 8mm thickness | 13*13cm | J3 Turret Platform | 169 | TRUE
|  |  | Plate per cm^2 8mm thickness | 8*8cm | J3 Spindle Bracket | 64 | TRUE
|  |  | Plate per cm^2 65mm thickness | 12*9cm | J4 Front Housing | 108 | TRUE
|  |  | Plate per cm^2 65mm thickness | 12*9cm | J4 Rear Housing | 108 | TRUE
|  |  | Plate per cm^2 25mm thickness | 9*9cm | J5 Motor Mount | 81 | TRUE
|  |  | Plate per cm^2 8mm thickness | 20*16cm | J4 Mount Right | 320 | TRUE
|  |  | Plate per cm^2 8mm thickness | 20*4cm | J4 Mount Left | 80 | TRUE
|  |  | Plate per cm^2 10mm thickness | 9*9cm | J4 Mount Center | 19 | TRUE
|  |  | Plate per cm^2 65mm thickness | 11*8cm | J5 Pipe Housing | 88 | TRUE
|  |  | Plate per cm^2 8mm thickness | 54*10cm | J5 Top Arm | 540 | TRUE
|  |  | Plate per cm^2 10mm thickness | 10*9cm | J5 Lead Screw Housing | 90 | TRUE
|  |  | Plate per cm^2 6mm thickness | 5*5cm | J5 Bearing Stopper | 25 | TRUE
|  |  | Plate per cm^2 10mm thickness | 8*6cm | J5 Idler Tension | 48 | TRUE
|  |  | As per cm 22.22mm diameter | 7/8inch | J5 Bearing Post | 4 | TRUE
|  |  | As per cm 82.55mm diameter | 3 1/4inch | J5 Spindle Housing | 4 | TRUE
|  |  | Plate per cm^2 8mm thickness | 10*10cm | J5 Turret Platform | 100 | TRUE
|  |  | As per cm 38.1mm diameter | 1 1/2inch | J5 Spindle Turret | 5 | TRUE
|  |  | Plate per cm^2 6mm thickness | 6*6cm | J5 Spindle Bracket | 36 | TRUE
|  |  | Plate per cm^2 25mm thickness | 9*4cm | J6 Motor Mount A | 36 | TRUE
|  |  | Plate per cm^2 25mm thickness | 9*4cm | J6 Motor Mount B | 36 | TRUE
|  | Stainless Steel | Pipe per cm 42.5mm diameter | SCH40 1.1/4inch | J4 Main Shaft | 31 | TRUE
|  | Filament | PLA+ 1.75mm | Strength 11-15kgf | 1kg | 3 | TRUE
4 | Fasteners | Bolts | Allen Bolt | M8 | 60mm | 2 | TRUE | 100%
|  |  | Allen Bolt | M8 | 20mm | 2 | TRUE
|  |  | Allen Bolt | M5 | 70mm | 19 | TRUE
|  |  | Allen Bolt | M5 | 60mm | 4 | TRUE
|  |  | Allen Bolt | M5 | 30mm | 28 | TRUE
|  |  | Allen Bolt | M5 | 20mm | 15 | TRUE
|  |  | Allen Bolt | M5 | 15mm | 8 | TRUE
|  |  | Allen Bolt | M4 | 45mm | 4 | TRUE
|  |  | Allen Bolt | M4 | 30mm | 4 | TRUE
|  |  | Allen Bolt | M4 | 25mm | 50 | TRUE
|  |  | Allen Bolt | M3 | 20mm | 18 | TRUE
|  |  | Allen Bolt | M3 | 15mm | 17 | TRUE
|  |  | Countersunk Bolt | M5 | 20mm | 37 | TRUE
|  |  | Countersunk Bolt | M4 | 20mm | 33 | TRUE
|  |  | Countesunk Bolt | M3 | 15mm | 31 | TRUE
|  |  | Set Screw | M5 | 25mm | 1 | TRUE
|  | Nut | Hex Nut | M5 | - | 59 | TRUE

## Timeline
TIMELINE 6-DOF WELDING ARM MANIPULATOR ROBOT PROJECT
[9 empty] | January | [11 empty] | February | [27 empty] | March | [30 empty] | April
Step Number | Step | Division | WBS Code | Activity | Is Done | PIC | Activity Count (Day) | Plan | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11
[8 empty] | Actual | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
1 | Design | Electrical | 2.1.3 | Evaluasi Desain PCB Kontroler Utama | TRUE | Alfon | 1 | P | TRUE
[7 empty] | 1 | A | TRUE
|  |  | 2.1.4 | Listing Komponen PCB Kontroler Utama | TRUE | Alfon | 1 | P | TRUE
[7 empty] | 1 | A | TRUE
|  |  | 3.1.2 | Desain Pengawatan Komponen Kontrol Pada Panel | TRUE | Alfon | 2 | P |  | TRUE | TRUE
[7 empty] | 2 | A |  | TRUE | TRUE
|  |  | 3.2.5 | Desain Hole Position Panel Kontrol | TRUE | Alfon | 1 | P | [5 empty] | TRUE
[7 empty] | 1 | A | [5 empty] | TRUE
|  |  | 4.1.1 | Desain Schematic Konektor Utama | TRUE | Alfon | 2 | P |  | TRUE | TRUE
[7 empty] | 2 | A |  | TRUE | TRUE
|  |  | 4.1.2 | Desain Board Konektor Utama | TRUE | Alfon | 2 | P |  | TRUE | TRUE
[7 empty] | 2 | A |  | TRUE | TRUE
|  |  | 4.1.3 | Evaluasi Desain Konektor Utama | TRUE | Alfon | 1 | P |  |  |  | TRUE
[7 empty] | 1 | A |  |  |  | TRUE
|  |  | 4.1.4 | Listing Komponen Konektor Utama | TRUE | Alfon | 1 | P |  |  |  | TRUE
[7 empty] | 1 | A |  |  |  | TRUE
|  | Mechanical | 1.2.4 | Analisis FEA untuk Mengetahui Kekuatan Desain Final | TRUE | Wildan | 4 | P | TRUE | TRUE | TRUE | TRUE
[7 empty] | 4 | A | TRUE | TRUE | TRUE | TRUE
|  |  | 1.3.1 | Perancangan Cable Management Robot | TRUE | Wildan | 7 | P |  |  |  |  | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 7 | A |  |  |  |  | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 1.3.2 | Perancangan Connector Housing Robot | TRUE | Wildan | 6 | P | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 6 | A | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 1.3.3 | Perancangan Cover Body | TRUE | Wildan | 6 | P | [21 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 6 | A | [21 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 1.4.1 | Pembongkaran dan Pengukuran MIG Welding | TRUE | Putra, Arsya | 2 | P | [35 empty] | TRUE | TRUE
[7 empty] | 2 | A | [35 empty] | TRUE | TRUE
|  |  | 1.4.2 | Perancangan Desain Mounting End Effector | TRUE | Putra, Arsya | 3 | P | [37 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [37 empty] | TRUE | TRUE | TRUE | [29 empty] | FALSE
|  |  | 1.4.3 | Perancangan Jig Machining Tangent | TRUE | Wildan | 3 | P | [14 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [14 empty] | TRUE | TRUE | TRUE
|  |  | 1.4.4 | Perancangan Jig Machining Perpendicular | TRUE | Wildan | 3 | P | [17 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [17 empty] | TRUE | TRUE | TRUE
2 | Purchasing | Electrical | 1.1.4 | Pembelian Keypad Teach Pendant | TRUE | Alfon | 4 | P | TRUE | TRUE | TRUE | TRUE
[7 empty] | 4 | A | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5 | Komponen Kontroler Utama | TRUE | Alfon | 3 | P |  |  | TRUE | TRUE | TRUE
[7 empty] | 3 | A |  |  | TRUE | TRUE | TRUE
|  |  | 3.2.3 | Komponen Panel Kontrol | TRUE | Alfon | 5 | P | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 5 | A | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 4.1.5 | Komponen Konektor Utama | TRUE | Alfon | 4 | P |  |  |  | TRUE | TRUE | TRUE |  | TRUE
[7 empty] | 4 | A |  |  |  | TRUE | TRUE | TRUE |  | TRUE
|  | Mechanical | 3.2.2 | Pembelian Materials Machining | TRUE | Wildan | 6 | P | [7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 6 | A | [7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.3.3 | Pembelian Components | TRUE | Wildan | 4 | P | [14 empty] | TRUE | TRUE | TRUE | TRUE
[7 empty] | 4 | A | [14 empty] | TRUE | TRUE | TRUE | TRUE
|  |  | 2.3.4 | Pembelian Fasteners | TRUE | Wildan | 4 | P | [14 empty] | TRUE | TRUE | TRUE | TRUE
[7 empty] | 4 | A | [14 empty] | TRUE | TRUE | TRUE | TRUE
3 | Manufacturing | Electrical | 1.2.4 | Pengujian Keypad | TRUE | Alfon | 1 | P |  |  |  |  | TRUE
[7 empty] | 1 | A |  |  |  |  | TRUE
|  |  | 1.4.4 | Pemasangan Top Case & Bottom Case | TRUE | Alfon | 1 | P |  |  |  |  | TRUE
[7 empty] | 1 | A |  |  |  |  | TRUE
|  |  | 2.1.6 | Pencetakan PCB Kontroler Utama | TRUE | Alfon | 9 | P |  |  |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE
[7 empty] | 14 | A |  |  |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.7 | Perakitan Komponen Kontroler Utama | TRUE | Alfon | 4 | P | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 4 | A | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
|  |  | 2.2.1 | Pengujian Daya Kontroler Utama | TRUE | Alfon | 3 | P | [16 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [16 empty] | TRUE | TRUE | TRUE
|  |  | 2.2.2 | Pengujian Komunikasi RS-232 Kontroler Utama | TRUE | Alfon | 3 | P | [19 empty] | TRUE |  | TRUE | TRUE
[7 empty] | 4 | A | [19 empty] | TRUE |  | TRUE | TRUE | TRUE
|  |  | 2.2.3 | Pengujian Pembacaan Encoder Kontroler Utama | TRUE | Alfon | 3 | P | [23 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [23 empty] | TRUE | TRUE | TRUE
|  |  | 2.2.4 | Pengujian Kontrol Motor Stepper Kontroler Utama | TRUE | Alfon | 1 | P | [26 empty] | TRUE
[7 empty] | 1 | A | [26 empty] | TRUE
|  |  | 2.2.5 | Pengujian Interface Kontroler Utama | TRUE | Alfon | 2 | P | [26 empty] | TRUE |  | TRUE
[7 empty] | 2 | A | [26 empty] | TRUE |  | TRUE
|  |  | 2.2.6 | Pengujian EEPROM Kontroler Utama | TRUE | Alfon | 3 | P | [29 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [29 empty] | TRUE | TRUE | TRUE
|  |  | 2.2.7 | Pengujian Emergency Stop Kontroler Utama | TRUE | Alfon | 1 | P | [31 empty] | TRUE
[7 empty] | 1 | A | [31 empty] | TRUE
|  |  | 2.2.8 | Pengujian Penuh | TRUE | Alfon | 2 | P | [32 empty] | TRUE | TRUE
[7 empty] | 2 | A | [32 empty] | TRUE | TRUE
|  |  | 2.3.2 | Pencetakan Bracket Kontroler Utama | TRUE | Gilar | 2 | P | [21 empty] | TRUE | TRUE
[7 empty] | 2 | A | [21 empty] | TRUE | TRUE
|  |  | 3.2.4 | Pengukuran Komponen Panel Kontrol | TRUE | Alfon | 2 | P |  |  |  |  | TRUE | TRUE
[7 empty] | 2 | A |  |  |  |  | TRUE | TRUE
|  |  | 3.3.1 | Pembuatan Hole Panel Kontrol | TRUE | Alfon | 3 | P | [9 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [9 empty] | TRUE | TRUE | TRUE
|  |  | 3.3.2 | Pemasangan Komponen Daya | TRUE | Alfon | 2 | P | [11 empty] | TRUE | TRUE
[7 empty] | 2 | A | [11 empty] | TRUE | TRUE
|  |  | 3.3.3 | Pemasangan Komponen Kontrol | TRUE | Alfon | 4 | P | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 4 | A | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
|  |  | 3.3.4 | Pengawatan Panel Kontrol | TRUE | Alfon, Imam | 6 | P | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 6 | A | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 4.1.6 | Pencetakan PCB Konektor Utama | TRUE | Yudho | 4 | P | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 4 | A | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
|  | Mechanical | 2.1.4.2 | Jig Tangent | TRUE | Wildan | 3 | P | [21 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [21 empty] | TRUE | TRUE | TRUE
|  |  | 2.1.4.3 | Jig Perpendicular | TRUE | Wildan | 3 | P | [24 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [24 empty] | TRUE | TRUE | TRUE
|  |  | 2.1.5.1 | J1 Base Plate | TRUE | Daffa | 10 | P |  |  |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 13 | A |  |  |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.2 | J1 Tension Bracket | TRUE | Putra, Arsya | 1 | P | TRUE
[7 empty] | 1 | A | TRUE
|  |  | 2.1.5.3 | J1 Base Bracket | TRUE | Devas | 5 | P | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 5 | A | [14 empty] | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.4 | J1 Spindle Housing | TRUE | Putra | 2 | P | [28 empty] | TRUE | TRUE
[7 empty] | 2 | A | [28 empty] | TRUE | TRUE
|  |  | 2.1.5.5 | J1 Spindle Turret | TRUE | Wildan | 1 | P | TRUE
[7 empty] | 1 | A | TRUE
|  |  | 2.1.5.6 | J1 Turret Platform | TRUE | Arsya | 10 | P |  |  |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 13 | A |  |  |  |  | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.7 | J1 Spindle Bracket | TRUE | Arsya | 8 | P | [7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 8 | A | [7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
|  |  | 2.1.5.8 | J2 Spindle Housing | TRUE | Putra, Arsya | 2 | P | [28 empty] | TRUE | TRUE
[7 empty] | 3 | A | [28 empty] | TRUE | TRUE | TRUE
|  |  | 2.1.5.9 | J2 Spindle Bracket | TRUE | Putra, Arsya | 3 | P | TRUE | [15 empty] | TRUE | TRUE
[7 empty] | 4 | A | TRUE | [15 empty] | TRUE | TRUE | TRUE
|  |  | 2.1.5.10 | J2 Motor Bracket Bottom | TRUE | Akbar | 2 | P | TRUE | [15 empty] | TRUE
[7 empty] | 2 | A | TRUE | [15 empty] | TRUE
|  |  | 2.1.5.11 | J2 Motor Support Bottom | TRUE | Devas, Akbar | 2 | P | TRUE | [16 empty] | TRUE
[7 empty] | 3 | A | TRUE | [16 empty] | TRUE | TRUE
|  |  | 2.1.5.12 | J2 Motor Bracket Top | TRUE | Devas | 2 | P | TRUE | [17 empty] | TRUE
[7 empty] | 2 | A | TRUE | [17 empty] | TRUE
|  |  | 2.1.5.13 | J2 Motor Support Top | TRUE | Devas | 2 | P | TRUE | [17 empty] | TRUE
[7 empty] | 2 | A | TRUE | [17 empty] | TRUE
|  |  | 2.1.5.14 | J2 Spindle Turret | TRUE | Wildan | 2 | P | [5 empty] | TRUE | [6 empty] | TRUE
[7 empty] | 2 | A | [5 empty] | TRUE | [6 empty] | TRUE
|  |  | 2.1.5.15 | J2 Bottom Arm | TRUE | Putra, Arsya | 8 | P | [7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 11 | A | [7 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.16 | J3 Spindle Housing | TRUE | Wildan | 1 | P | TRUE
[7 empty] | 1 | A | TRUE
|  |  | 2.1.5.17 | J3 Spindle Turret | TRUE | Putra, Arsya | 2 | P | [17 empty] | TRUE | TRUE
[7 empty] | 2 | A | [17 empty] | TRUE | TRUE
|  |  | 2.1.5.18 | J3 Turret Platform | TRUE | Putra, Arsya | 6 | P | [9 empty] | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 6 | A | [9 empty] | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
|  |  | 2.1.5.19 | J3 Spindle Bracket | TRUE | Putra | 3 | P | TRUE | [16 empty] | TRUE | TRUE
[7 empty] | 3 | A | TRUE | [16 empty] | TRUE | TRUE
|  |  | 2.1.5.20 | J4 Front Housing | TRUE | Putra, Arsya | 4 | P | [28 empty] | TRUE | TRUE | TRUE | TRUE
[7 empty] | 4 | A | [28 empty] | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.21 | J4 Rear Housing | TRUE | Putra, Arsya | 4 | P | [30 empty] | TRUE | TRUE | TRUE | TRUE
[7 empty] | 4 | A | [30 empty] | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.22 | J5 Motor Mount | TRUE | Putra | 2 | P | [21 empty] | TRUE | TRUE
[7 empty] | 2 | A | [21 empty] | TRUE | TRUE
|  |  | 2.1.5.23 | J4 Mount Right | TRUE | Putra | 2 | P |  | TRUE | TRUE
[7 empty] | 2 | A |  | TRUE | TRUE
|  |  | 2.1.5.24 | J4 Mount Left | TRUE | Arsya, Putra | 1 | P | TRUE
[7 empty] | 1 | A | TRUE
|  |  | 2.1.5.25 | J4 Mount Center | TRUE | Arsya | 2 | P |  | TRUE | TRUE
[7 empty] | 2 | A |  | TRUE | TRUE
|  |  | 2.1.5.26 | J5 Pipe Housing | TRUE | Putra, Arsya | 2 | P | [23 empty] | TRUE | TRUE
[7 empty] | 2 | A | [23 empty] | TRUE | TRUE
|  |  | 2.1.5.27 | J5 Top Arm | TRUE | Putra, Arsya | 6 | P | [9 empty] | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 9 | A | [9 empty] | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.28 | J5 Lead Screw Housing | TRUE | Arsya | 2 | P | TRUE | TRUE
[7 empty] | 2 | A | TRUE | TRUE
|  |  | 2.1.5.29 | J5 Bearing Stopper | TRUE | Arsya | 1 | P |  |  |  | TRUE
[7 empty] | 1 | A |  |  |  | TRUE
|  |  | 2.1.5.30 | J5 Idler Tension | TRUE | Putra | 2 | P | TRUE | TRUE
[7 empty] | 2 | A | TRUE | TRUE
|  |  | 2.1.5.31 | J5 Bearing Post | TRUE | Putra, Arsya | 11 | P |  |  |  | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 14 | A |  |  |  | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | 2.1.5.32 | J5 Spindle Housing | TRUE | Putra, Arsya | 2 | P | [23 empty] | TRUE | TRUE
[7 empty] | 2 | A | [23 empty] | TRUE | TRUE
|  |  | 2.1.5.33 | J5 Turret Platform | TRUE | Putra | 4 | P | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
[7 empty] | 4 | A | [11 empty] | TRUE | TRUE |  | TRUE | TRUE
|  |  | 2.1.5.34 | J5 Spindle Turret | TRUE | Putra, Arsya | 2 | P | [25 empty] | TRUE | TRUE
[7 empty] | 2 | A | [25 empty] | TRUE | TRUE
|  |  | 2.1.5.35 | J5 Spindle Bracket | TRUE | Putra | 2 | P | [11 empty] | TRUE | TRUE
[7 empty] | 2 | A | [11 empty] | TRUE | TRUE
|  |  | 2.1.5.36 | J6 Motor Mount A | TRUE | Putra, Arsya | 2 | P | [14 empty] | TRUE | TRUE
[7 empty] | 2 | A | [14 empty] | TRUE | TRUE
|  |  | 2.1.5.37 | J6 Motor Mount B | TRUE | Putra, Arsya | 3 | P | [16 empty] | TRUE | TRUE | TRUE
[7 empty] | 3 | A | [16 empty] | TRUE | TRUE | TRUE
|  |  | 2.1.5.38 | J4 Main Shaft | TRUE | Putra, Arsya | 3 | P | [25 empty] | TRUE | TRUE |  | TRUE
[7 empty] | 3 | A | [25 empty] | TRUE | TRUE |  | TRUE
|  |  | 2.2.2.2 | J3 Pulley | TRUE | Putra, Arsya | 2 | P | [63 empty] | TRUE | TRUE
[7 empty] | 2 | A | [63 empty] | TRUE | TRUE
|  |  | 2.2.2.3 | Proses Assembly | TRUE | Wildan, Putra, Arsya | 18 | P | [46 empty] | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | [6 empty] | TRUE | TRUE | TRUE
[7 empty] | 18 | A | [46 empty] | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | [6 empty] | TRUE | TRUE | TRUE
|  |  | 2.2.2.4 | Troubleshoot | TRUE | Wildan | 13 | P | [46 empty] | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE
[7 empty] | 13 | A | [46 empty] | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE